# Complete Event Execution Plan

# 1. PLANNING

1.1 Preparation

- List of Schools

- Rekki of all Eco Centres (safety, facilities, hospital proximity)

- Mapping: Schools ↔ Eco Centers, Eco Centers ↔ Guest Lecturers, Coordinators ↔ Schools/Eco centers

1.2 Event Date Finalization

- Finalize schedule with School, Eco center, Guest lecturer, Forest Department

1.3 Permissions & Compliance

- Written permissions from Forest Department

- Inform local RFO/Beat Office

- Collect parent consent forms

- Share Do’s & Don’ts with schools

- Prepare emergency contact sheet

1.4 SOP Definition

- Pre-event checks (bus reporting, inspection, attendance, safety briefing)

- During event protocols (trail walk, waste management, group control)

- Return & closing (attendance, feedback, summary)

- Post-event reporting and social media guidelines

1.5 Logistics & Material Planning

- Prepare gifts, activities & stationery

- Waste bags, first aid, student ID stickers, drinking water

- Backup: alternate lecturers, eco centers, indoor activity

1.6 Communication Planning

- WhatsApp groups (NGO+Teachers, NGO+Forest, NGO+Driver)

- Assign NGO roles: Transport, School lead, Forest liaison, Safety, Documentation

# 2. SALES / OUTREACH

2.1 School Engagement

- Outreach and pipeline creation

- Share eco center options, activity list, pricing, FAQ

2.2 Partnerships

- Coordination with DEO, BEO, cluster heads

- Request official circular

2.3 Marketing

- Social media promotions

- Promo video, brochure

- CSR outreach

# 3. EXECUTION (Event Day)

3.1 Pre-departure

- Bus reporting & inspection

- Attendance checks

- Student ID stickers

- Grouping students

3.2 At the Eco Center

- Welcome, safety briefing

- Nature trail walk

- Guest lecturer session

- NGO activities & interviews

3.3 Hygiene & Safety

- Cleanliness and waste collection

- First aid availability

- Hydration monitoring

3.4 Contingencies

- Replacement lecturer / NGO backup

- Backup bus support

- Indoor activity for bad weather

3.5 Return

- Final attendance check

- Handing over students to school

# 4. POST-EVENT

4.1 Feedback

- From schools, teachers, students

- Testimonies on letterheads

4.2 Documentation

- Bi-weekly report, monthly news report

- Photos/videos (as permitted)

- Final summary to Forest Department

4.3 Administration

- Invoice preparation

- Update master tracker

- Thank-you letters

4.4 Social Media

- Only permitted content

- Share after approvals